## Slide 1: CARE AUSTRALIA PROGRAM QUALITY FRAMEWORK
The PQF looks at three stages of the project cycle: concept/proposal/design; inception/implementation/monitoring; and review/evaluation. For each stage, it sets out key consultation and programming processes for Australian-funded projects; proposed mandatory steps; tools and guidance (noting where these are existing or planned), and proposed roles within CARE Australia and the CO.
The following slides provide an overview of the PQF, with flowcharts summarising programming processes, key program quality steps, and relevant outputs at each stage. For full detail on roles and processes, please refer to the full PQ Framework and associated documents.
If you have any queries or suggestions, please check with CARE Australia’s Quality and Impact team (QI).

## Slide 2: CA PQ FRAMEWORK – overview of concept/proposal/design stage
A joint plan for design process is agreed between CO and CP, to set out key steps, inputs, scheduling.
If using consultants, TOR are to be cleared and signed off by CO in consultation with CP before proceeding to recruit.
If not using specific donor format, the design will be based on an agreed CA format.
CA arranges appraisal of draft design and peer review with CO; feedback is then consolidated and followup agreed with CO.
Following finalisation of design by CO/CA, PCIM reviews and signs off budget; PE IP approves final design to submit to donor.
Brief design review concall identifies any outstanding quality or process issues and any followup needed by CA/CO.
JOINT PLANNING | AGREEING TOR | DESIGN FORMAT | APPRAISAL AND PEER REVIEW | FINAL SIGNOFF | DESIGN REVIEW
Agreed design plan
Agreed TOR
Agreed design format
Appraisal comment
Approved final design
Design review writeup
Processes
PQ Steps
Outputs

## Slide 3: CA PQ FRAMEWORK – overview of inception/implementation stage
CO recruits and briefs staff, with CA providing necessary info on Australian requirem’ts.
CO conducts inception workshop or process for staff and stakeholders; CA attends or provides inputs.
CO develops TOR for baseline for consultation with CA, signoff by ACD-P; CA reviews draft baseline report, CO finalises.
Within Annual Planning, CO leads brief Review and Learning process, documented (by CA if in attendance) for annual reporting.
Reports and annual plans for donor provided by CO, reviewed / cleared by CA (including financials) , signed off by PE and sent to donor.
CO oversees M&E of implement’n, expenditure; CA monitors including through PSMVs which provide basis for agreed followup.
STAFF RECRUITMENT | INCEPTION PROCESSES | SETTING BASELINE | ANNUAL REVIEW/ REFLECTION | PROJECT REPORTS AND PLANS | ONGOING MONITORING
Induction complete
Inception complete
Baseline TOR and report
Brief review document
Project reports, annl plans
PSMV reports
Processes
PQ Steps
Outputs

## Slide 4: CA PQ FRAMEWORK – overview of review/ evaluation stage
A joint plan for evaluation process is agreed between CO and CA, to set out key steps, inputs, scheduling, roles.
If using consultants, TOR are to be developed by CO with review from CA and signed off by ACD-P before proceeding to recruit.
CO oversees eval plan, methodol’gy, field research and in-country consultationswith support from CA as agreed.
Draft report from CO is reviewed by CA and consolidated feedback provided for followup by CO and consultants.
Following finalisation of report by CO/ CA, PE IP approves final report to submit to donor. CO prepares brief management response.
CA lodges final report on CI Online library and summary on CA website; includes summary in annual reporting on evaluations undertaken.
JOINT PLANNING | AGREEING TOR | EVALUATION PLANNING / IMPLEMENT’N | REVIEW AND FEEDBACK | FINAL SIGNOFF & MANAGEMENT RESPONSE | DISSEMINAT’N & REPORTING
Agreed joint plan
Agreed TOR
Agreed evaluat’n plan
Docu-mented feedback
Approved final report
Eval report online
Processes
PQ Steps
Outputs